## Event Response - Dry Run
Event Response - Dry Run |  |  |  | All analysis to be done on run-off portfolio
Use Ian as target event |  |  |  | Use existing data saved in LiveEvents folder for analysis. We can download NHC/AIR data if it's not in the folder.
CFAN data is not available anymore. We have to use existing data.
One analysis should be done in less than a day
The entire dry run should take maximum 5 days.
All analysis are for Florida only (including 9/30 analysis)
The dry run should include end reports
The report should include starting point, end results, external sources, other event info
Every single step should be documented including downloading the event data
Every single step should be timed and tracked
Time taken to fix mistakes should also be counted separately in from of the task
Time taken to find data sources should be counted separately
14
No | Analysis No | Date of analysis |  | Analysis
1 | 1 | 2022-09-23 | TD9 becomes HU Ian | Track analysis
2 |  |  |  | industry loss analysis
3 |  |  |  | event loss by deal by portfolio
4 |  |  |  | event parameters
5 |  |  |  | industry loss by event by county
6 |  |  |  | Create report
7 | 2 | 2022-09-26 | HU Ian enters GOM | Track analysis
8 |  |  |  | industry loss analysis
9 |  |  |  | event loss by deal by portfolio
10 |  |  |  | event parameters
11 |  |  |  | industry loss by event by county
12 |  |  |  | detailed exposure analysis - total exposed TIV - using COU
13 |  |  |  | detailed exposure analysis - total exposed limit - using COU
14 |  |  |  | Create report
15 | 3 | 2022-09-27 | Forecast track passes through Tampa (High exposure zone) | detailed exposure analysis - TIV by windspeed, TIV by storm surge depth
16 |  |  |  | Track analysis
17 |  |  |  | industry loss analysis
18 |  |  |  | event loss by deal by portfolio
19 |  |  |  | event parameters
20 |  |  |  | industry loss by event by county
21 |  |  |  | AIR, RMS SSEs - loss by deal by portfolio
22 |  |  |  | Create report
23 | 4 | 2022-09-28 | Landfall south of Tampa in Lee County | detailed exposure analysis - TIV by windspeed, TIV by storm surge depth
24 |  |  |  | GU loss, GR loss - with buffer - with bins of storm surge depth
25 |  |  |  | GU loss, GR loss - without buffer - with bins of storm surge depth
26 |  |  |  | Track analysis
27 |  |  |  | industry loss analysis
28 |  |  |  | event loss by deal by portfolio
29 |  |  |  | event parameters
30 |  |  |  | industry loss by event by county
31 |  |  |  | AIR, RMS SSEs - loss by deal by portfolio
32 |  |  |  | Create report
33 | 5 | 2022-09-30 | Landfall in South Carolina | detailed exposure analysis - TIV by windspeed, TIV by storm surge depth
34 |  |  |  | AIR Shapefile - detailed exposure analysis
35 |  |  |  | GU loss, GR loss - with buffer - with bins of storm surge depth
36 |  |  |  | GU loss, GR loss - without buffer - with bins of storm surge depth
37 |  |  |  | Track analysis
38 |  |  |  | industry loss analysis
39 |  |  |  | event loss by deal by portfolio
40 |  |  |  | event parameters
41 |  |  |  | industry loss by event by county
42 |  |  |  | AIR, RMS SSEs - loss by deal by portfolio
43 |  |  |  | Create report