## Timeline
Priority
In Progress
Not Started
Reserch and Development + Priority
Section | Topic | Sub Topic | Efforts | Timeline | Priority
Validation Part | Reasonability Rules | Gathered AIR and RMS Pre-defined Rules/Rule Descriptions | 0.5 |  | Done
|  | Rule Table Schema | 1 | 2023-01-16 | Done
|  | Convert Descriptive Rule into sql Table Rule (AIR) | 3 | 2023-01-20 | Done
|  | Convert Descriptive Rule into sql Table Rule (RMS) | 2 |  | Not Started
|  | Add Rules of Secondary Modifiers |  |  | Not Started
|  | Add Rules of Financial Terms |  |  | Not Started
|  | Categorize Rules into two category, 1. Informative Rule 2. Actionable Rule |  |  | Not Started
|  | Fill the Error Flag message | 2 | 2023-01-24 | Not Started
|  | Insert Rule table to SQL DB | 1 | 2023-01-25 | Done
| SQL | Write query to Loop over the Rules for each locations | 2 | 2023-01-25 | Done
|  | Create Flag Message Table | 1 |  | Not Started
|  | Define Accuracy Summary Table Schema | 1 |  | Done
|  | Validate SQL Query with one Deal by Testing Key Rules | 2-3 |  | Done
|  | Summarize the Flag locations in Numbers and Total percentages |  | 2023-01-25 | Done
|  | Store the Accuracy Summary to DB |  | 2023-01-25 | Done
| VBA Code | VBA Code to execute Validation Rule Query and Show results to DashBoard | 1 |  | Done
BenchMark | Cohort Analysis by cost per SQFT | modified python script to extract data from DB | 2 | 2023-01-13 | 3
python script to store costperSQFT analysis results for each individual and all deals
|  | Compare the Cedent based on Year using Peril/Region | 1 | 2023-01-13 | 4
|  | Validate Cohort Summary | 2 | 2023-01-13 | 5
Data Population | SQL | Exposure Meta Table Schema | 1 | 2023-01-05 | Done
|  | Query to Populate the Exposure Meta Table from Exposure DB Info and Exposure Set List Table | 1 | 2023-01-05 | Done
| Fill up the ExposureMeta Table | List out the Exposure Db Names | 1 |  | In Progress
|  | Fill up the version and Type of Exposure Data | 1 |  | In Progress
|  | Select Exposure Sets for each Exposure DB | 1 |  | In Progress
| Validation | Validate the Inputs and it's update from Job | 2 | 2023-01-06 | Done
DQ Summary | SQL | Table Schema for Data Quality tables | 1 | 2023-01-05 | Done
|  | Insert Stored Procedures | 3-4 | 2023-01-05 | Done
|  | Insert Master Stored Procedure to Execute all the Insert Sps | 2 | 2023-01-05 | Done
|  | Create Job to Loop over Meta Table and run Master Sp | 1 | 2023-01-05 | Done
|  | Call Stored Procedures | 2 | 2023-01-10 | Done
|  | Master Stored Procedure to fetch data from DQ tables | 1 | 2023-01-10 | Done
|  | Modify all insert stored procedure to be able run across SQL Server | 1 |  | Done
| VBA | VBA code to fill exposure meta table | 1 | 2023-01-05 | Done
|  | VBA Code to Retrive the DQ Summary from DQ Tables | 1 | 2023-01-12 | Done
| Year Built | Revised Year Built Ranges | 1 |  | Done
|  | Modification on Insert Stored Procedures | 1 |  | Done
| Secondary Modifiers | Add new 10 Tables of Secodary Modifiers | 0.5 |  | Done
|  | Define Table Schema of Database Tables | 0.5 |  | Done
|  | Create Insert Stored Procedures for inserting data to Database Tables | 1 |  | Done
|  | Validate Insert Stored Procedures by Query | 1 |  | Done
|  | Create Call Stored Procedures for calling data from Database Tables | 1 |  | Done
|  | Validate Call Stored Procedures by Execl DashBoard | 1 |  | Done
Industry Data | SQL | Define table schema for Price per SQFT and Average Property Value | 1 |  | Done
|  | Figure out way to connect Industry tables with Meta Table | 1 |  | Done
|  | Create Stored Procedures to Insert Data from CEDE DB to Industry Tables | 1 |  | Done
|  | Validate Stored Procedures of Inserting | 1 |  | Done
|  | Create Stored Procedures to Auto trigger Insert/Update of Industry Tables if new entry in Meta Table | 1
|  | Validate auto Stored Procedures | 1
Visualization | Excel Dash Board | Gathered all key attributes DQ Summary YoY data | 0.5 |  | Done
|  | Create Pivot chart for YoY Data | 0.5 |  | Done
|  | Cohort chart for Price per SQFT data | 1 |  | Done
|  | Top 5 States Cohort Chart for Price per SQFT by plotting Box plot | 1 |  | Done
|  | Gathered YoY data for Secondary Modifiers | 0.5 |  | Done
|  | Create Pivot chart of YoY Data of Secondary Modifiers | 0.5 |  | Done
| QGIS | Create Chart using Roof Cover and Roof Geometry Data | 0.5 |  | Done
|  | Chart containing Pie Chart which categories different types of Roof Cover and Roof Geometry | 0.5 |  | Done
| Choropleth Map in Python | Pie Charts on US Map for Roof cover and Roof Geometry Data | 1 |  | Done
|  | YoY TIV Pct Change | 1 |  | Done
|  | Price per SQFT data on State and County level | 1 |  | Done
|  | YoY Average Property Value Pct Change | 1 |  | Done
|  | Bechmarking with Industry by plotting Box plot on US Map | 1 |  | Done
|  | Bechmarking using textured lines on all plots | 1 |  | Done
| Investigation | Amfam showing huge YoY% Changes in Average Property Value and in Price per SQFT | 1
|  | Revised Filteres on data | 1 |  | Done
|  | Investigate States with negative YoY% Change | 1 |  | Done
|  | Move on Progressive Data, few states was having high postive and negative YoY% Change | 1 |  | Done
|  | Investigate California and Nebraska State Data | 1 |  | Done
| Python | Dynamic Python Inputs Data | 1
|  | Create SQL Queries for Price per SQFT and Average Property Value | 2 |  | Done
|  | Dynamic Industry Data through query | 0.5 |  | Done
|  | Dynamic python script by mapping data column with query's data columns | 1 |  | Done
|  | Create Python function for creating choropleth map dynamically | 1 |  | In Progress
Augmetation | External Data | Gather External Data | ?? |  |  | 1
|  | Validation Rule to Validate External Data | ??
|  | Methodology to Augment Data | ??
|  | Save the Augmented Data into Dummy Database | ??
| Validate | Create the DQ Summary of Dummy Database | ??
Scoring | Completeness | Define Scoring Table Schema for Completeness | 0.5 |  | Done
|  | Come up with Scoring Methodology for Completeness of data | 5 |  | Done
| Validation | Define Scoring Table Schema using Validation Rules | ?? |  | In Progress
|  | Come up with Scoring Methodology for Validation of data using Validation Scoring | ?? |  | In Progress
Sensitivity Analysis using combination on primary attributes
Analyze sensitivity analysis results and come up scoring
| Accuracy | Come up with Scoring Methodology for Accuracy Scoring
| SQL | Query to fill up Scoring table for Completeness of data | 0.5
|  | Query to fill up Scoring table for Accuracy of data | ??
Updates | Comments/Suggestions | Add the Exposure Vintage Date and Type into Exposure DB info table |  | 2023-01-05 | Done
|  | Change the Schema of Exposure Meta Table to add Exposure Vintage Date |  | 2023-01-05 | Done
|  | Add Column for Sponsor ID to Exposure Meta Table |  | 2023-01-05
|  | Added "All perils" clause to all insert DQ table |  | 2023-01-06 | Done
|  | Added PerilSetCode Column to All DQ Tables |  | 2023-01-10 | Done
|  | Modified all the Insert SP by setting Peril as perilCode and added PerilSetCode |  | 2023-01-10 | Done
|  | Modified Validation Rules query to consider case of RMS coded exposure |  | 2023-01-13 | Done
|  | Added 3 Columns(which indicates total percentage of Loc, Con and TIV) to Validatio Rule Result table |  | 2023-01-13 | Done
|  | Modified the Validation Query to Add above three columns |  | 2023-01-13 | Done
|  | Add "List" as attributeType in Rule Table |  | 2023-01-20 | Done
|  | Modified the Validation Query to include "List" as attribute Variable |  | 2023-01-20 | Done

## Benchmark (hidden)
[7 empty] | Sp insert query update | Schema | Need to Create New Query | Need to store in DB |  | DQ Exhibits
Exposure Meta Table |  |  | AIRDQ_TIVbyPerilandConstruction |  | AIRConstruction Table = AIRReference.dbo.tAIRConstruction |  |  | Done |  | 1 | AIRDQ_TIVbyPeril | AIRDQ_TIVbyPerils | Peril table
Column_name |  | data type | Column_name | data type | Column_name | data type |  |  |  | 0 |  | AIRDQ_TIVbyGeoCodeMatchLevel
ID | DB Exposure Set SID | int | ID | int | AIRConstructionCode | int |  |  |  | 0 |  | AIRDQ_TIVbyStateCountry
DBName |  | nvarchar(255) | exposureID | int | ConstructionCategory | varchar |  |  |  | 0 |  | AIRDQ_TIVbyOccupancyCategory | Occupancy table
Exposure Set Name |  | nvarchar(255) | Peril | varchar | AIRConstruction | varchar |  |  |  | 0 |  | AIRDQ_TIVbyConstructionCategory | Construction table
Exposure Set SID |  | int | Construction Code | int | Description | varchar |  |  |  | 0 |  | AIRDQ_TIVbyYearBuiltRange
TIV |  | float | TIV | float | [5 empty] | 0 |  | AIRDQ_TIVbyNumberOfStories
Loc Count |  | int | Loc Count | int | [5 empty] | 0 |  | AIRDQ_TIVbyFloorArea
Con Count |  | int | Con Count | int | [5 empty] | 0 |  | AIRDQ_TIVbyOccupancyTypeCode | Occupancy table
Floor Area |  | float | FloorArea | float | AIRPeril Table = AIRReference.dbo.tPeril |  |  |  |  | 0 |  | AIRDQ_TIVbyConstructionTypeCode | Construction table
Present Perils |  | nvarchar(255) |  |  | Column_name | data type |  |  |  | 0 |  | AIRDQ_TIVperSQFTbyFLCounty
[5 empty] | PerilCode | varchar |  |  |  | 0 |  | AIRDQ_TIVbyRoofAge
[5 empty] | Peril | varchar |  | Done | 0 | 1 | AIRDQ_TIVbyPeril_GeoCodeMatch | AIRDQ_TIVbyPerilsandGeoCodeMatch
|  |  | AIRDQ_TIVbyPerilandOccupancy |  | Description | varchar |  | Done | 0 | 1 | AIRDQ_TIVbyPeril_Occupancy | AIRDQ_TIVbyPerilsandOccCategory | Peril and Occupancy table
|  |  | Column_name | data type | PerilSetCode | int |  | Done | 0 | 1 | AIRDQ_TIVbyPeril_Construction | AIRDQ_TIVbyPerilsandConCategory | Peril and Construction table
Combining Table |  |  | ID | int | PerilDisplayGroup | varchar
Column_name |  | data type | exposureID | int | IsEnabled | bit |  | Done | 1 | 1 | AIRDQ_TIVbyPeril_YearBuilt | AIRDQ_TIVbyPerilandYearBuiltRange | Peril table
Deal Year |  | int | Peril | varchar | ModRulePerilSetCode | int |  | Done | 1 | 1 | AIRDQ_TIVbyPeril_FloorArea | AIRDQ_TIVbyPerilandFloorArea | Peril table
Deal Name |  | nvarchar(255) | Occupancy Code | int | IsReinsurance | bit |  | Done | 1 | 1 | AIRDQ_TIVbyPeril_RoofAge | AIRDQ_TIVbyPerilandRoofAge | Peril table
Peril |  | nvarchar(255) | TIV | float | UIOrder | tinyint |  | Done | 1 | 1 | AIRDQ_TIVbyPeril_Stories | AIRDQ_TIVbyPerilandNumberOfStories | Peril table
DB Name |  | nvarchar(255) | Loc Count | int |  |  |  | Done | 1 | 1 | AIRDQ_BldgValueperSQFTbyPeril | AIRDQ_BldgValueperSQFT | Peril table
Exposure Set Name |  | nvarchar(255) | Con Count | int |  |  |  | Done | 1 | 1 | AIRDQ_TIVbyPeril_StateCountry | AIRDQ_TIVbyPeril_StateCountry | Peril table
Exposure Vintage |  | nvarchar(255) | FloorArea | float
Fillingup the MetaData Table
Take the DB Name
Run the List of Exposure Sets Query
Look if DB Name in the MetaData Table
if it is not there there than Run Insert Query to add the DB info into meta data
take ExposureMetaID
if it is there than look for Exposure SET SID and DB name and take It's ID as ExposureMetaID

## Tables
Secondary Modifiers | Option ID is AIR Code.
Roof Year Built |  | Year Built
Unknown |  | Unknown
<5 yr |  | <1925
5-10 yrs |  | 1925-1960
10-20 yr |  | 1961-1975
>20 yrs |  | 1976-1995
1996-2001
Window Protection | Option ID | 2002-2005
| 0 | 2006-2012
No Protection | 1 | 2012>
Non-Engineered Shutters | 2
Engineered Shutters | 3
Roof Geometry | Option ID
Unknown/default | 0
Flat | 1
Gable end without bracing | 2
Hip | 3
Complex | 4
Stepped | 5
Shed | 6
Mansard | 7
Gable end with bracing | 8
Pyramid | 9
Gambrel | 10
Roof Deck Attachment | Option ID
Unknown/default | 0
Screws/Bolts | 1
Nails/Staples | 2
Adhesive/epoxy | 3
Structurally Connected | 4
6d nails @ 6" spacing, 12" o.c. | 5
8d nails @ 6" spacing, 12" o.c. | 6
8d nails @ 6" spacing, 6" o.c. | 7
Roof Covering | Option ID
Unknown/default | 0
Asphalt Shingles | 1
Wooden Shingles | 2
Clay/Concrete Tiles | 3
Light Metal Panels | 4
Slate | 5
Built-up Roof With Gravel | 6
Single Ply Membrane | 7
Standing Seam Metal Roofs | 8
Built-Up Roof Without Gravel | 9
Single Ply Membrane Ballasted | 10
Hurricane Wind-Rated Roof Coverings | 11

## Stored Procedures (hidden)
Sr. No. | SP Names | Table Names | Created | Validate
1 | sp_AIRDQ_Insert_TIVbyPeril_FloorArea | AIRDQ_TIVbyPeril_FloorArea | Yes | Yes
2 | sp_AIRDQ_Insert_TIVbyPeril | AIRDQ_TIVbyPeril | Yes | Yes
3 | sp_AIRDQ_Insert_TIVbyPeril_Construction | AIRDQ_TIVbyPeril_Construction | Yes | Yes
4 | sp_AIRDQ_Insert_TIVbyPeril_GeoCodeMatch | AIRDQ_TIVbyPeril_GeoCodeMatch | Yes | Yes
5 | sp_AIRDQ_Insert_TIVbyPeril_Occupancy | AIRDQ_TIVbyPeril_Occupancy | Yes | Yes
6 | sp_AIRDQ_Insert_TIVbyPeril_YearBuiltRange | AIRDQ_TIVbyPeril_YearBuiltRange | Yes | Yes
7 | sp_AIRDQ_Insert_TIVbyPeril_RoofAge | AIRDQ_TIVbyPeril_RoofAge | Yes | Yes
8 | sp_AIRDQ_Insert_TIVbyPeril_NumberOfStories | AIRDQ_TIVbyPeril_Stories | Yes | Yes
9 | sp_AIRDQ_Insert_TIVbyPeril_StateCountry | AIRDQ_TIVbyPeril_StateCountry | Yes | Yes
10 | sp_AIRDQ_Insert_BldgValueperSQFT | AIRDQ_BldgValueperSQFTbyPeril | Yes | Yes
11 | sp_AIRDQ_Insert |  | Yes | Yes
12 | sp_AIRDQ_call_TIVbyConstruction | AIRDQ_TIVbyPeril_Construction | Yes | Yes
13 | sp_AIRDQ_call_TIVbyConstructionCode | AIRDQ_TIVbyPeril_Construction | Yes | Yes
14 | sp_AIRDQ_call_TIVbyFloorArea | AIRDQ_TIVbyPeril_FloorArea | Yes | Yes
15 | sp_AIRDQ_call_TIVbyGeoCodeMatch | AIRDQ_TIVbyPeril_GeoCodeMatch | Yes | Yes
16 | sp_AIRDQ_call_TIVbyOccupancy | AIRDQ_TIVbyPeril_Occupancy | Yes | Yes
17 | sp_AIRDQ_call_TIVbyOccupancyCode | AIRDQ_TIVbyPeril_Occupancy | Yes | Yes
18 | sp_AIRDQ_call_TIVbyPeril_Construction | AIRDQ_TIVbyPeril_Construction | Yes | Yes
19 | sp_AIRDQ_call_TIVbyPeril_ConstructionCode | AIRDQ_TIVbyPeril_Construction | Yes | Yes
20 | sp_AIRDQ_call_TIVbyPeril_FloorArea | AIRDQ_TIVbyPeril_FloorArea | Yes | Yes
21 | sp_AIRDQ_call_TIVbyPeril_GeoCodeMatch | AIRDQ_TIVbyPeril_GeoCodeMatch | Yes | Yes
22 | sp_AIRDQ_call_TIVbyPeril_Occupancy | AIRDQ_TIVbyPeril_Occupancy | Yes | Yes
23 | sp_AIRDQ_call_TIVbyPeril_OccupancyCode | AIRDQ_TIVbyPeril_Occupancy | Yes | Yes
24 | sp_AIRDQ_call_TIVbyPeril_RoofAge | AIRDQ_TIVbyPeril_RoofAge | Yes | Yes
25 | sp_AIRDQ_call_TIVbyPeril_StateCountry | AIRDQ_TIVbyPeril_StateCountry | Yes | Yes
26 | sp_AIRDQ_call_TIVbyPeril_Stories | AIRDQ_TIVbyPeril_Stories | Yes | Yes
27 | sp_AIRDQ_call_TIVbyPeril_YearBuiltRange | AIRDQ_TIVbyPeril_YearBuiltRange | Yes | Yes
28 | sp_AIRDQ_call_TIVbyPerils | AIRDQ_TIVbyPeril | Yes | Yes
29 | sp_AIRDQ_call_TIVbyRoofAge | AIRDQ_TIVbyPeril_RoofAge | Yes | Yes
30 | sp_AIRDQ_call_TIVbyStateCountry | AIRDQ_TIVbyPeril_StateCountry | Yes | Yes
31 | sp_AIRDQ_call_TIVbyStories | AIRDQ_TIVbyPeril_Stories | Yes | Yes
32 | sp_AIRDQ_call_TIVbyYearBuiltRange | AIRDQ_TIVbyPeril_YearBuiltRange | Yes | Yes

## List of Stored Procedures
Sr.No. | Stored Procedure Names | Sp Type | Table Name | Main Column | Attribute Type | Table Schema Defined? | Stored Procedure Tested? | Added to Master Insert SP? | Comments
1 | sp_AIRDQ_call_BldgValueperSQFT | Call | AIRDQ_BldgValueperSQFTbyPeril | BuildingValueperSQFT | Primary |  | Yes | Not Applicable
2 | sp_AIRDQ_call_TIVbyConstruction | Call | AIRDQ_TIVbyPeril_Construction | ConstructionCode | Primary |  | Yes | Not Applicable
3 | sp_AIRDQ_call_TIVbyConstructionCode | Call | AIRDQ_TIVbyPeril_Construction | ConstructionCode | Primary |  | Yes | Not Applicable
4 | sp_AIRDQ_call_TIVbyFloorArea | Call | AIRDQ_TIVbyPeril_FloorArea | FloorAreaRange | Primary |  | Yes | Not Applicable
5 | sp_AIRDQ_call_TIVbyGeoCodeMatch | Call | AIRDQ_TIVbyPeril_GeoCodeMatch | GeoMatchLevel | Primary |  | Yes | Not Applicable
6 | sp_AIRDQ_call_TIVbyOccupancy | Call | AIRDQ_TIVbyPeril_Occupancy | OccupancyCode | Primary |  | Yes | Not Applicable
7 | sp_AIRDQ_call_TIVbyOccupancyCode | Call | AIRDQ_TIVbyPeril_Occupancy | OccupancyCode | Primary |  | Yes | Not Applicable
8 | sp_AIRDQ_call_TIVbyPeril_Construction | Call | AIRDQ_TIVbyPeril_Construction | ConstructionCode | Primary |  | Yes | Not Applicable
9 | sp_AIRDQ_call_TIVbyPeril_ConstructionCode | Call | AIRDQ_TIVbyPeril_Construction | ConstructionCode | Primary |  | Yes | Not Applicable
10 | sp_AIRDQ_call_TIVbyPeril_FloorArea | Call | AIRDQ_TIVbyPeril_FloorArea | FloorAreaRange | Primary |  | Yes | Not Applicable
11 | sp_AIRDQ_call_TIVbyPeril_GeoCodeMatch | Call | AIRDQ_TIVbyPeril_GeoCodeMatch | GeoMatchLevel | Primary |  | Yes | Not Applicable
12 | sp_AIRDQ_call_TIVbyPeril_Occupancy | Call | AIRDQ_TIVbyPeril_Occupancy | OccupancyCode | Primary |  | Yes | Not Applicable
13 | sp_AIRDQ_call_TIVbyPeril_OccupancyCode | Call | AIRDQ_TIVbyPeril_Occupancy | OccupancyCode | Primary |  | Yes | Not Applicable
14 | sp_AIRDQ_call_TIVbyPeril_RoofAge | Call | AIRDQ_TIVbyPeril_RoofAge | RoofAge | Secondary |  | Yes | Not Applicable
15 | sp_AIRDQ_call_TIVbyPeril_RoofCovering | Call | AIRDQ_TIVbyPeril_RoofCovering | RoofCover | Secondary |  | Yes | Not Applicable
16 | sp_AIRDQ_call_TIVbyPeril_RoofDeckattachment | Call | AIRDQ_TIVbyPeril_RoofDeckAttachment | RoofDeckAttach | Secondary |  | Yes | Not Applicable
17 | sp_AIRDQ_call_TIVbyPeril_RoofGeometry | Call | AIRDQ_TIVbyPeril_RoofGeometry | RoofGeometry | Secondary |  | Yes | Not Applicable
18 | sp_AIRDQ_call_TIVbyPeril_StateCounty | Call | AIRDQ_TIVbyPeril_StateCounty | County | Primary |  | Yes | Not Applicable
19 | sp_AIRDQ_call_TIVbyPeril_Stories | Call | AIRDQ_TIVbyPeril_Stories | NoOfStoriesRange | Secondary |  | Yes | Not Applicable
20 | sp_AIRDQ_call_TIVbyPeril_WindowProtection | Call | AIRDQ_TIVbyPeril_WindowProtection | WindowProtection | Secondary |  | Yes | Not Applicable
21 | sp_AIRDQ_call_TIVbyPeril_YearBuiltRange | Call | AIRDQ_TIVbyPeril_YearBuilt | YearBuiltRange | Primary |  | Yes | Not Applicable
22 | sp_AIRDQ_call_TIVbyPerils | Call | AIRDQ_TIVbyPeril | Peril | Primary |  | Yes | Not Applicable
23 | sp_AIRDQ_call_TIVbyRoofAge | Call | AIRDQ_TIVbyPeril_RoofAge | RoofAge | Secondary |  | Yes | Not Applicable
24 | sp_AIRDQ_call_TIVbyRoofCovering | Call | AIRDQ_TIVbyPeril_RoofCovering | RoofCover | Secondary |  | Yes | Not Applicable
25 | sp_AIRDQ_call_TIVbyRoofDeckAttachment | Call | AIRDQ_TIVbyPeril_RoofDeckAttachment | RoofDeckAttach | Secondary |  | Yes | Not Applicable
26 | sp_AIRDQ_call_TIVbyRoofGeometry | Call | AIRDQ_TIVbyPeril_RoofGeometry | RoofGeometry | Secondary |  | Yes | Not Applicable
27 | sp_AIRDQ_call_TIVbyStateCounty | Call | AIRDQ_TIVbyPeril_StateCounty | County | Primary |  | Yes | Not Applicable
28 | sp_AIRDQ_call_TIVbyStories | Call | AIRDQ_TIVbyPeril_Stories | NoOfStoriesRange | Primary |  | Yes | Not Applicable
29 | sp_AIRDQ_call_TIVbyWindowProtection | Call | AIRDQ_TIVbyPeril_WindowProtection | WindowProtection | Secondary |  | Yes | Not Applicable
30 | sp_AIRDQ_call_TIVbyYearBuiltRange | Call | AIRDQ_TIVbyPeril_YearBuilt | YearBuiltRange | Primary |  | Yes | Not Applicable
31 | sp_AIRDQ_call_ValidationResults | Call | AIRDQ_ReasonabilityRulesResult | RuleID |  |  | Yes | Not Applicable
32 | sp_AIRDQ_call_ValidationSummary | Call | AIRDQ_ReasonabilityRulesResult | RuleID |  |  | Yes | Not Applicable
33 | sp_AIRDQ_call_YoY_Data | Call |  |  | Primary |  | Yes | Not Applicable
34 | sp_AIRDQ_ExposureMetaTable | Insert | AIRDQ_ExposureMetaData |  |  |  | Yes | Not Applicable
35 | sp_AIRDQ_ExposureSetsFromDB | Insert | CEDE |  |  |  | Yes | Not Applicable
37 | sp_AIRDQ_GetExposureSets | Insert | CEDE |  |  |  | Yes | Not Applicable
38 | sp_AIRDQ_Insert | Insert |  |  |  |  | Yes | Not Applicable
39 | sp_AIRDQ_Insert_BldgValueperSQFT | Insert | AIRDQ_BldgValueperSQFTbyPeril | BuildingValueperSQFT | Primary |  | Yes | Yes
40 | sp_AIRDQ_Insert_Industry_AveragePropertyValue | Insert | AIRDQ_Industry_AveragePropertyValue | AveragePropertyValue | Primary |  | Yes
41 | sp_AIRDQ_Insert_Industry_BldgValueperSQFT | Insert | AIRDQ_Industry_BldgValueperSQFTbyPeril | BuildingValueperSQFT | Primary |  | Yes | Yes
42 | sp_AIRDQ_Insert_TIVbyPeril | Insert | AIRDQ_TIVbyPeril | Peril | Primary |  | Yes | Yes
43 | sp_AIRDQ_Insert_TIVbyPeril_Construction | Insert | AIRDQ_TIVbyPeril_Construction | ConstructionCode | Primary |  | Yes | Yes
44 | sp_AIRDQ_Insert_TIVbyPeril_FloorArea | Insert | AIRDQ_TIVbyPeril_FloorArea | FloorArea | Primary |  | Yes | Yes
45 | sp_AIRDQ_Insert_TIVbyPeril_GeoCodeMatch | Insert | AIRDQ_TIVbyPeril_GeoCodeMatch | GeoMatchLevel | Primary |  | Yes | Yes
46 | sp_AIRDQ_Insert_TIVbyPeril_NumberOfStories | Insert | AIRDQ_TIVbyPeril_Stories | NoOfStoriesRange | Primary |  | Yes | Yes
47 | sp_AIRDQ_Insert_TIVbyPeril_Occupancy | Insert | AIRDQ_TIVbyPeril_Occupancy | OccupancyCode | Primary |  | Yes | Yes
48 | sp_AIRDQ_Insert_TIVbyPeril_RoofAge | Insert | AIRDQ_TIVbyPeril_RoofAge | RoofAge | Secondary |  | Yes | Yes
49 | sp_AIRDQ_Insert_TIVbyPeril_RoofCovering | Insert | AIRDQ_TIVbyPeril_RoofCovering | RoofCover | Secondary |  | Yes | Yes
50 | sp_AIRDQ_Insert_TIVbyPeril_RoofDeckAttachment | Insert | AIRDQ_TIVbyPeril_RoofDeckAttachment | RoofDeckAttach | Secondary |  | Yes | Yes
51 | sp_AIRDQ_Insert_TIVbyPeril_RoofGeometry | Insert | AIRDQ_TIVbyPeril_RoofGeometry | RoofGeometry | Secondary |  | Yes | Yes
52 | sp_AIRDQ_Insert_TIVbyPeril_StateCounty | Insert | AIRDQ_TIVbyPeril_StateCounty | County | Secondary |  | Yes | Yes
53 | sp_AIRDQ_Insert_TIVbyPeril_WindowProtection | Insert | AIRDQ_TIVbyPeril_WindowProtection | WindowProtection | Secondary |  | Yes | Yes
54 | sp_AIRDQ_Insert_TIVbyPeril_YearBuiltRange | Insert | AIRDQ_TIVbyPeril_YearBuilt | YearBuiltRange | Primary |  | Yes | Yes
55 | sp_AIRDQ_ReasonabilityRules | Insert | AIRDQ_ReasonabilityRulesResult | RuleID |  |  | Yes | Yes
56 | sp_AIRDQ_Insert_TIVbyPeril_GlassPercent | Insert | AIRDQ_TIVbyPeril_GlassPercent |  |  |  | Yes | Yes
57 | sp_AIRDQ_Insert_TIVbyPeril_RoofAnchorage | Insert | AIRDQ_TIVbyPeril_RoofAnchorage |  |  |  | Yes | Yes
58 | sp_AIRDQ_Insert_TIVbyPeril_RoofDeck | Insert | AIRDQ_TIVbyPeril_RoofDeck |  |  |  | Yes | Yes
59 | sp_AIRDQ_Insert_TIVbyPeril_WallType | Insert | AIRDQ_TIVbyPeril_WallType |  |  |  | Yes | Yes
60 | sp_AIRDQ_call_TIVbyGlassPercent | Call | AIRDQ_TIVbyPeril_GlassPercent |  |  |  | Yes | Not Applicable
61 | sp_AIRDQ_call_TIVbyRoofDeck | Call | AIRDQ_TIVbyPeril_RoofDeck |  |  |  | Yes | Not Applicable
62 | sp_AIRDQ_call_TIVbyRoofAnchorage | Call | AIRDQ_TIVbyPeril_RoofAnchorage |  |  |  | Yes | Not Applicable
63 | sp_AIRDQ_call_TIVbyWallType | Call | AIRDQ_TIVbyPeril_WallType |  |  |  | Yes | Not Applicable

## List of Tables
Sr. No. | Table Names
1 | AIRDQ_BldgValueperSQFTbyPeril
2 | AIRDQ_ExposureMetaData
3 | AIRDQ_Industry_AveragePropertyValue
4 | AIRDQ_Industry_BldgValueperSQFTbyPeril
5 | AIRDQ_ReasonabilityRules
6 | AIRDQ_ReasonabilityRulesResult
7 | AIRDQ_Scoring
8 | AIRDQ_TIVbyPeril
9 | AIRDQ_TIVbyPeril_Construction
10 | AIRDQ_TIVbyPeril_FloorArea
11 | AIRDQ_TIVbyPeril_GeoCodeMatch
12 | AIRDQ_TIVbyPeril_Occupancy
13 | AIRDQ_TIVbyPeril_RoofAge
14 | AIRDQ_TIVbyPeril_RoofCovering
15 | AIRDQ_TIVbyPeril_RoofDeckAttachment
16 | AIRDQ_TIVbyPeril_RoofGeometry
17 | AIRDQ_TIVbyPeril_StateCountry
18 | AIRDQ_TIVbyPeril_Stories
19 | AIRDQ_TIVbyPeril_WindowProtection
20 | AIRDQ_TIVbyPeril_YearBuilt
21 | AIRDQ_ValidationRules_NullValues

## Deals List
Sr. No. | CEDE Name | Deal Year | Deal Name | Exposure Vintage Type | Exposure Vintage Date | Version

## Sheet1 (hidden)
Section | Topic | Sub Topic | Efforts | Timeline | Priority | Completed
Industry Data | SQL | Define table schema for Price per SQFT and Average Property Value | 1 |  |  | Done
|  | Figure out way to connect Industry tables with Meta Table | 1 |  |  | Done
|  | Create Stored Procedures to Insert Data from CEDE DB to Industry Tables | 1 |  |  | Done
|  | Validate Stored Procedures of Inserting | 1 |  |  | Done
|  | Create Stored Procedures to Auto trigger Insert/Update of Industry Tables if new entry in Meta Table | 1
|  | Validate auto Stored Procedures | 1
Visualization | Excel Dash Board | Gathered all key attributes DQ Summary YoY data | 0.5 |  |  | Done
|  | Create Pivot chart for YoY Data | 0.5 |  |  | Done
|  | Cohort chart for Price per SQFT data | 1 |  |  | Done
|  | Top 5 States Cohort Chart for Price per SQFT by plotting Box plot | 1 |  |  | Done
|  | Gathered YoY data for Secondary Modifiers | 0.5 |  |  | Done
|  | Create Pivot chart of YoY Data of Secondary Modifiers | 0.5 |  |  | Done
| QGIS | Create Chart using Roof Cover and Roof Geometry Data | 0.5 |  |  | Done
|  | Chart containing Pie Chart which categories different types of Roof Cover and Roof Geometry | 0.5 |  |  | Done
| Choropleth Map in Python | Pie Charts on US Map for Roof cover and Roof Geometry Data | 1 |  |  | Done
|  | YoY TIV Pct Change | 1 |  |  | Done
|  | Price per SQFT data on State and County level | 1 |  |  | Done
|  | YoY Average Property Value Pct Change | 1 |  |  | Done
|  | Bechmarking with Industry by plotting Box plot on US Map | 1 |  |  | Done
|  | Bechmarking using textured lines on all plots | 1 |  |  | Done
| Investigation | Amfam showing huge YoY% Changes in Average Property Value and in Price per SQFT | 1
|  | Revised Filteres on data | 1 |  |  | Done
|  | Investigate States with negative YoY% Change | 1 |  |  | Done
|  | Move on Progressive Data, few states was having high postive and negative YoY% Change | 1 |  |  | Done
|  | Investigate California and Nebraska State Data | 1 |  |  | Done
| Python | Dynamic Python Inputs Data | 1
|  | Create SQL Queries for Price per SQFT and Average Property Value | 2 |  |  | Done
|  | Dynamic Industry Data through query | 0.5 |  |  | Done
|  | Dynamic python script by mapping data column with query's data columns | 1 |  |  | Done
|  | Create Python function for creating choropleth map dynamically | 1 |  |  | In Progress
DQ Summary | SQL | Modify all insert stored procedure to be able run across SQL Server | 1 |  |  | Done
| Year Built | Revised Year Built Ranges | 1 |  |  | Done
|  | Modification on Insert Stored Procedures | 1 |  |  | Done
| Secondary Modifiers | Add new 4 Tables of Secodary Modifiers | 0.5 |  |  | Done
|  | Define Table Schema of Database Tables | 0.5 |  |  | Done
|  | Create Insert Stored Procedures for inserting data to Database Tables | 1 |  |  | Done
|  | Validate Insert Stored Procedures by Query | 1 |  |  | Done
|  | Create Call Stored Procedures for calling data from Database Tables | 1 |  |  | Done
|  | Validate Call Stored Procedures by Execl DashBoard | 1 |  |  | Done